## Sheet1
Process | Sub Process | Activities | Role/Responsibility | Template
PM | Initiation/Planning | - Assign PM/PL to the project. | SDD | -
|  | - Analyse the initial (pre-sales) estimation for fitment of the project. | PM/PL
|  | - PM/PL, Resource Manager, SDD shall discuss and agree upon the required Human Resource for the project. | PM/PL, SDD, RM | -
|  | - Request TimeSheet and SharePoint to the Admin Team | PM/PL | Create Project Form
|  | - Provide new TimeSheet and SharePoint access for the requested project | Admin Team
|  | - Request Version Control Repository (SVN/Git) to the Process Team | PM/PL | Email
|  | - Provide Version Control Repository (SVN/Git) to the requested project | QA
|  | - Use the Minimum CI List document to check the required configuration items for the project |  | AW_SCM_MinCIList.xls to be revised
|  | - Prepare Project Plan Schedule | PM/PL
|  | - Project Plan Schedule shall be reviewed by SA/Technical Lead | SA/Technical Lead
|  | - Prepare Project Kick Off presentation | PM/PL
|  | - Send email notification to the members of the Project about their selection to work for the Project | PM/PL
|  | - Send Kick Off meeting request to all the stakeholders (including IT Department) | PM/PL
|  | - Conduct the Kick Off meeting | PM/PL
|  | - Request Development, Test Servers and other required hardware/network resources to the IT department | PM/PL | email
|  | - Provide the request Development, Test Servers and other required hardware/network resources to the project | IT Department
|  | - Prepare Development Plan | PM/PL | Check this template
|  | - Prepare Test Plan | Test Lead | Test Plan Template
|  | - Request UAT/Production servers minimum a month before the required start date to the IT Department | PM/PL
|  | - Provide the requested UAT/Production servers to the project | IT Department